## avp
Defect ID | NUM_AVP_EXT | Summary | Oceane | Component | CCU_Version | Phase | Gravity | Urgency | CCS Severity | Impact | Record Type | Status | Current owner | Entity in charge | Detected on Date | Author | Target Release | Resolution | Planned delivery Date | Effective delivery Date | Delay | Validation Date | Closing Date | Release
4315 | CCS-24560 | [FCC] Old value of MediaDeviceAddresss ( tel number ) on flexible Agent connection | 1311620520 | AIS | CCU_6.0 | PRODUCTION | G1 - Major | U0 - Blocking |  | Traitement d'appel | Anomaly | Fixed | CosmoCom | Cosmocom | 2013-11-26 | CZND8315 | 6.0 | update 8
4150 | CCS-24089 | [FCC][6.0][VCS] the DTMF are not sent in SIP INFO packets while "SIPUseINFOForDTMF" registery key is set to 1 |  | VCS | CCU_6.0 | PRODUCTION | G2 - Medium | U1 - Urgent |  | Traitement d'appel | Anomaly | Control | CosmoCom | Cosmocom | 2013-10-04 | MJVQ8661 | 6.0 | update 8 | 2013-11-04 | 2013-11-30 |  | 2014-01-31
3440 | CCS-23951 | [CCU 6.0] skill weight is not respected | 1309203497 | AIS | CCU_6.0 | PRODUCTION | G2 - Medium | U0 - Blocking |  | Syst譥 | Anomaly | Fixed | CosmoCom | Cosmocom | 2013-09-12 | dhbn7811 | 6.0 | Update 8 | 2014-02-12
3422 | CCS-23898 | [CCU 6.0][A2A] transfert between agent includes '¦' |  | VCS | CCU_6.0 | PRODUCTION | G0 - Critical | U1 - Urgent |  | Traitement d'appel | Anomaly | Control | CosmoCom | Cosmocom | 2013-09-06 | dhbn7811 | 6.0 | Update 9 | 2013-12-05
3303 | CCS-23021 | [CCU 6.0][WebAdmin API] WebAdmin API: Agent deletion |  | WebAdmin | CCU_6.0 | Qualification MOE | G2 - Medium | U2 - Medium |  | Selfcare | Anomaly | Pending | FT DPS QUALIF | Cosmocom | 2013-07-08 | rlnb9407 | 6.0 | Update 9 | 2014-01-01
3295 | CCS-23409 | [CCU 6.0] Outgoing call with callingNumber_:¦ |  | VCS | CCU_6.0 | PRODUCTION | G0 - Critical | U1 - Urgent |  | Traitement d'appel | Anomaly | Control | CosmoCom | Cosmocom | 2013-07-03 | FJRF1046 | 6.0 | Update 9 | 2013-12-05
3260 | CCS-23306 | [FCC] many loops of MaxCallDurationTime |  | VCS | CCU_6.0 | PRODUCTION | G2 - Medium | U1 - Urgent |  | Traitement d'appel | Anomaly | Control | CosmoCom | Cosmocom | 2013-06-18 | CZND8315 | 6.0 | update 9 | 2014-01-01
3248 | CCS-23253 | [FCC] RTP jitter / RTP loss warning level |  | VCS | CCU_6.0 | PRODUCTION | G2 - Medium | U2 - Medium |  | Voix | Information Request | Correction | CosmoCom | Cosmocom | 2013-06-12 | CZND8315 | 6.1 | 6.1 | 2014-07-01 | 2013-11-30 |  | 2014-01-31
3236 | CCS-23200 | [FCC] VCS wrong active calls values perfmon / syslog | 1308525792 | VCS | CCU_6.0 | PRODUCTION | G2 - Medium | U0 - Blocking |  | Syst譥 | Anomaly | Control | CosmoCom | Cosmocom | 2013-06-06 | CZND8315 | 6.0 | Update 9 | 2014-01-01
3201 | CCS-22931 | [CCU 6.0] Differences between Web Admin and AgentWS web service when changing an agent password |  | APS | CCU_6.0 | Qualification MOE | G1 - Major | U1 - Urgent |  | FlexibleWorkspace | Anomaly | Fixed | CosmoCom | Cosmocom | 2013-05-03 | XJJT7505 | 6.0 | Update 8 | 2013-11-04 |  |  |  |  | G1R5C8
3196 | CCS-22890 | [CCU 6.0] Summer time and records dates and hours displayed in CosmoCorder |  | CosmoCorder | CCU_6.0 | PRODUCTION | G1 - Major | U1 - Urgent |  | FlexibleWorkspace | Anomaly | Fixed | CosmoCom | Cosmocom | 2013-04-26 | XJJT7505 | 6.0 | Update8 | 2013-12-01 | 2013-11-30 |  | 2014-01-31
3185 | CCS-22823 | [RTR] Inconsistency of indicators in RTR console | 1305951600 | RTR | CCU_6.0 | PRODUCTION | G0 - Critical | U1 - Urgent |  | FlexibleWorkspace | Anomaly | Control | FT DEPFS | Cosmocom | 2013-04-18 | dhbn7811 | 6.0 | Update 6 | 2013-12-01 | 2013-11-30 |  | 2014-01-31
3166 | CCS-22748 | [CCU V6.0] Talktime in agent to agent call |  | VCS | CCU_6.0 | PRODUCTION | G2 - Medium | U2 - Medium |  | InfoCentre | Anomaly | Control | CosmoCom | Cosmocom | 2013-04-10 | MJVQ8661 | 6.0 | HF60-37404 | 2013-12-01 | 2013-11-30 |  | 2014-01-31
3105 | CCS-22576 | [FCC] A2A transfert fails if tenant's phone ANI is empty |  | VCS | CCU_6.0 | PRODUCTION | G2 - Medium | U2 - Medium |  | SIP | Anomaly | Correction | FT DPS QUALIF | Cosmocom | 2013-03-19 | TKWQ7008 | 6.1 | 6.1 | 2014-07-01 | 2013-11-30 |  | 2014-01-31
3088 | CCS-22510 | [FCC] LoggingServer bad files |  | Logging Server | CCU_6.0 | PRODUCTION | G1 - Major | U1 - Urgent |  | InfoCentre | Anomaly | Control | CosmoCom | Cosmocom | 2013-03-12 | CZND8315 | 6.0 | Update 6 | 2013-09-01 | 2013-11-30 |  | 2014-01-31
3081 | CCS-22468 | [CCU 6.0] Exchange warning "ADLIB: Failed to Create Tenant's Theme!" |  | TenantProvisionner | CCU_6.0 | PRODUCTION | G2 - Medium | U2 - Medium |  | Mail | Anomaly | Fixed | FT DPS QUALIF | Cosmocom | 2013-03-08 | TKWQ7008 | 6.1
2953 | CCS-22081 | [CCU 6.0] SIP INVITE : translatedNumber too long |  | VCS | CCU_6.0 | Qualification MOE | G2 - Medium | U2 - Medium |  | Synth賥 Reconnaissance vocale | Anomaly | Control | CosmoCom | Cosmocom | 2013-01-10 | FJRF1046 | 6.0 | HF60-37404 | 2013-05-15 | 2013-06-20 |  | 2014-01-31
2947 | CCS-22072 | [FCC] VCS: IMS Crash 001B:7C84CDE2 | 1301562314 | VCS | CCU_6.0 | PRODUCTION | G1 - Major | U2 - Medium |  | Voix | Anomaly | Correction | CosmoCom | Cosmocom | 2013-01-09 | CZND8315 | 6.1 | 6.1 | 2014-07-01 | 2013-11-30 |  | 2014-01-31
2901 | CCS-21817 | [CCU6.0] Rebranding dashboard |  | CosmoDashboard | CCU_6.0 | Qualification MOE | G3 - Minor | U2 - Medium |  | CosmoDashboard | Information Request | Fixed | FT DPS QUALIF | Cosmocom | 2012-11-26 | BOBY8420 | 6.0 | Update 6 | 2013-12-01 | 2013-11-30 |  | 2014-01-31
2837 | CCS-21621 | [FCC 6.0] AIS perfmon counter "comfaulted agents" , bad value |  | AIS | CCU_6.0 | PRODUCTION | G3 - Minor | U2 - Medium |  | Syst譥 | Anomaly | Fixed | CosmoCom | Cosmocom | 2012-10-12 | CZND8315 | 6.0 | Update 7 | 2014-07-01 | 2013-11-30 |  | 2014-01-31
2758 | CCS-20955 | [CCU 6.0][Ajax API] Mandatory fields for callback creation using ajax API |  | API AJAX | CCU_6.0 | Qualification MOE | G2 - Medium | U2 - Medium | Service impact | FlexibleWorkspace | Anomaly | Fixed | CosmoCom | Cosmocom | 2012-07-11 | xjjt7505 | 6.0 | Update 6 (HF60-36781) | 2013-12-01 | 2013-11-30 |  | 2014-01-31
2694 | CCS-20641 | [FCC] PushOLTPDataToDW failed sometimes |  | CosmoAnalyst | CCU_6.0 | PRODUCTION | G2 - Medium | U2 - Medium | Non-critical impact | CosmoAnalyst | Anomaly | Fixed | CosmoCom | Cosmocom | 2012-05-25 | CZND8315 | 6.0 | Update 6 | 2013-01-01 | 2013-11-30 |  | 2014-01-31
2691 | CCS-20611 | [CCU 6.0][Ajax API] Country code and area code mismatch |  | API AJAX | CCU_6.0 | PRODUCTION | G1 - Major | U2 - Medium | Minimal impact | FlexibleWorkspace | Anomaly | Correction | CosmoCom | Cosmocom | 2012-05-22 | xjjt7505 | 6.1 |  | 2012-12-01 | 2013-11-30 |  | 2014-01-31 |  | G1R4C2
2679 | CCS-20543 | [CCU 6.0][Ajax API] AgentService AsyncConfig Webservice doesn't provide timezone offset |  | API AJAX | CCU_6.0 | Qualification MOE | G1 - Major | U1 - Urgent | Minimal impact | FlexibleWorkspace | Anomaly | Fixed | CosmoCom | Cosmocom | 2012-05-14 | mwmf2787 | 6.0 | Update 5 | 2012-10-15 | 2013-03-27 |  | 2014-01-31 |  | G1R1C4
2549 | CCS-19626 | Agent mailbox directories localization |  | WebAdmin | CCU_6.0 | Qualification MOE | G2 - Medium | U2 - Medium | Non-critical impact | Mail | Information Request | Fixed | CosmoCom | Cosmocom | 2012-01-30 | tkwq7008 | 6.0 | Update 5 | 2012-10-15 | 2013-03-27
2371 | CCS-18635 | [CCU v6] Wrong system variables line.XXX for SIP incoming calls |  | VCS | CCU_6.0 | Qualification MOE | G3 - Minor | U3 - Non Urgent | Minimal impact | Voix | Anomaly | Control | CosmoCom | Cosmocom | 2011-09-09 | fjrf1046 | 6.0 | Update 5 | 2012-10-15 | 2013-03-27 |  |  | 2014-01-29
2366 | CCS-18612 | [CCU 6.0] Agent statistics in CosmoDashboard reports |  | CosmoDashboard | CCU_6.0 | Qualification MOE | G3 - Minor | U3 - Non Urgent | Minimal impact | CosmoDashboard | Information Request | Correction | CosmoCom | Cosmocom | 2011-09-06 | xjjt7505 | 6.1 | 6.1 | 2012-12-01 | 2013-11-30 |  | 2014-01-31
2310 | CCS-18123 | [CCU5.1] Differences between RTR and queue statistics |  | RTR | CCU_6.0 | PRODUCTION | G2 - Medium | U1 - Urgent | Non-critical impact | Wallboard | Anomaly | Control | CosmoCom | Cosmocom | 2011-06-30 | boby8420 | 6.0 | Update 8 | 2013-03-01 | 2013-11-30 |  | 2014-01-31
1969 |  | Mail deleted from public folder still seen as "Call waiting" in RTR |  | MCS | CCU_6.0 | Qualification MOE | G1 - Major | U2 - Medium |  | Mail | Anomaly | Fixed | CosmoCom | Cosmocom | 2010-07-28 | tkwq7008 | 6.1 |  | 2014-07-01
1863 | CCS-14350 | False error log when an agent hangs up right after answering an email |  | MCS | CCU_6.0 | Qualification MOE | G3 - Minor | U2 - Medium | Non-critical impact | Mail | Anomaly | Correction | CosmoCom | Cosmocom | 2010-04-22 | tkwq7008 | 6.1 | 6.1 | 2012-12-01 | 2013-11-30 |  | 2014-01-31